## Dashboard
OCM Implementation Dashboard | [5 empty] | DASHBOARD GUIDE
Auto-populated from worksheet data | [5 empty] | This dashboard auto-populates
from all other worksheets.
OVERALL OCM HEALTH |  |  | STAKEHOLDER SUMMARY
Metric | Score | Status | Strategy | Count | % | Update source sheets to
CSF Average |  |  | Manage Closely |  |  | refresh these metrics.
Maturity Score |  |  | Keep Satisfied
|  |  | Keep Informed |  |  | STATUS INDICATORS:
IMPLEMENTATION PROGRESS |  |  | Monitor |  |  | On Track = Score ≥4
Status | Count | % |  |  |  | Monitor = Score 3-4
Complete |  |  | ADKAR GAP SUMMARY |  |  | At Risk = Score <3
In Progress |  |  | Gap Type | Count | Priority
Not Started |  |  | Awareness
At Risk |  |  | Desire
Knowledge
Ability
RISK SUMMARY |  |  | Reinforcement
Level | Count | Action
High (15-25) |  | Immediate | RESISTANCE STATUS
Medium (7-14) |  | Plan needed | Status | Count | %
Low (1-6) |  | Monitor | Open/New
In Progress
Resolved

## Implementation Roadmap
Implementation Roadmap | [6 empty] | INSTRUCTIONS
Track OCM implementation
Phase | Activity | Description | Owner | Start | End | Status | across 5 phases, 25 activities.
Phase 1: Initiation | 1.1 Define Change | Document what is changing and why |  |  |  | Not Started
| 1.2 Identify Sponsor | Secure executive sponsorship |  |  |  | Not Started | HOW TO USE:
| 1.3 Form OCM Team | Assemble change management resources |  |  |  | Not Started | 1. Assign Owner
| 1.4 Stakeholder ID | Identify key stakeholder groups |  |  |  | Not Started | 2. Set Start/End dates
| 1.5 Business Case | Document benefits and ROI |  |  |  | Not Started | 3. Update Status (dropdown)
Phase 2: Assessment | 2.1 Readiness Assessment | Evaluate organizational readiness |  |  |  | Not Started
| 2.2 Stakeholder Analysis | Complete power/interest mapping |  |  |  | Not Started | STATUS OPTIONS:
| 2.3 Impact Assessment | Analyze change impacts |  |  |  | Not Started | • Not Started
| 2.4 Risk Assessment | Identify OCM-specific risks |  |  |  | Not Started | • In Progress
| 2.5 ADKAR Baseline | Establish baseline scores |  |  |  | Not Started | • Complete
Phase 3: Planning | 3.1 OCM Strategy | Define overall approach |  |  |  | Not Started | • Delayed
| 3.2 Communication Plan | Develop messaging |  |  |  | Not Started | • At Risk
| 3.3 Training Plan | Design curriculum |  |  |  | Not Started
| 3.4 Sponsorship Plan | Plan sponsor activities |  |  |  | Not Started
| 3.5 Resistance Plan | Mitigation strategies |  |  |  | Not Started
Phase 4: Execution | 4.1 Launch Comms | Begin awareness campaign |  |  |  | Not Started
| 4.2 Sponsor Activities | Execute sponsor plan |  |  |  | Not Started
| 4.3 Deliver Training | Conduct sessions |  |  |  | Not Started
| 4.4 Manage Resistance | Address issues |  |  |  | Not Started
| 4.5 Monitor Adoption | Track KPIs |  |  |  | Not Started
Phase 5: Sustainment | 5.1 Reinforcement | Recognition and rewards |  |  |  | Not Started
| 5.2 Embed in Systems | Update processes |  |  |  | Not Started
| 5.3 Knowledge Transfer | Transition to BAU |  |  |  | Not Started
| 5.4 Lessons Learned | Document learnings |  |  |  | Not Started
| 5.5 Close OCM | Formal closure |  |  |  | Not Started

## ADKAR Assessment
ADKAR Assessment | [7 empty] | INSTRUCTIONS
Rate each ADKAR element 1-5
Stakeholder/Group | A | D | K | A | R | Total | Priority Gap
Executive Leadership | [7 empty] | A = Awareness (why)
Middle Management | [7 empty] | D = Desire (want to)
Front-line Supervisors | [7 empty] | K = Knowledge (how)
End Users - Group A | [7 empty] | A = Ability (can do)
End Users - Group B | [7 empty] | R = Reinforcement (sustain)
IT Support
HR/Training | [7 empty] | RATING SCALE:
Partners | [7 empty] | 1 = Very Low
2 = Low
3 = Moderate
4 = High
5 = Very High
Priority Gap = lowest score
Focus interventions there.

## Stakeholder Analysis
Stakeholder Analysis | [9 empty] | ROLE TEMPLATES (Reference) |  |  |  | INSTRUCTIONS
[10 empty] | Role Template | Power | Interest | Suggested Key Messages | HOW TO USE:
Name | Role Template | Department | Power | Interest | Current | Desired | Key Messages | Strategy | Owner | Executive Sponsor | High | High | Strategic alignment, ROI, timeline | 1. Enter stakeholder Name
[10 empty] | Senior Leadership | High | Medium | Business case, resource needs, risks | 2. Select Role Template
[10 empty] | Middle Manager | Medium | High | Team impacts, timeline, support needed | → Power auto-fills
[10 empty] | Front-line Supervisor | Medium | High | Daily operations, team concerns, training | → Interest auto-fills
[10 empty] | End User - Heavy Impact | Low | High | What changes, training, support available | → Key Messages auto-fills
[10 empty] | End User - Light Impact | Low | Medium | Overview, timeline, where to get help | → Strategy auto-calculates
[10 empty] | IT Support Staff | Medium | High | Technical details, support procedures | 3. Set Current/Desired state
[10 empty] | HR/Training Team | Medium | Medium | Training needs, policy updates | 4. Assign Owner
[10 empty] | Finance/Procurement | Medium | Low | Budget, procurement, compliance
[10 empty] | External Partner | Low | Medium | Partnership impacts, coordination | You can override auto-filled
[10 empty] | Union Representative | Medium | High | Employee impacts, consultation process | values if needed.
[10 empty] | Customer (if impacted) | Low | High | Service changes, benefits, timeline
STRATEGY LOGIC:
High Pwr + High Int → Manage Closely
High Pwr + Low Int → Keep Satisfied
Low Pwr + High Int → Keep Informed
Low Pwr + Low Int → Monitor

## Communication Plan
Communication Plan | [6 empty] | INSTRUCTIONS
Plan communications
ID | Message/Topic | Audience | Channel | Sender | Date | Status
C001 | Change Announcement | All Employees | Town Hall | Exec Sponsor |  | Planned | THE 5 RIGHTS:
C002 | Leadership Briefing | Senior Leaders | Meeting | Project Sponsor |  | Planned | • Right Message
C003 | Manager Toolkit | Managers | Email+Portal | OCM Lead |  | Planned | • Right Audience
C004 | Progress Updates | All Stakeholders | Newsletter | PM |  | Planned | • Right Channel
C005 | [6 empty] | • Right Time
C006 | [6 empty] | • Right Sender
C007
C008
C009
C010
C011
C012
C013
C014
C015
C016
C017
C018
C019
C020
C021
C022
C023
C024

## Training Plan
Training Plan | [8 empty] | INSTRUCTIONS
Plan training by role
ID | Course | Audience | Format | Duration | Date | Enrolled | Complete | Status
T001 | Change Overview | Leaders | Workshop | 2 hrs |  |  |  | Planned | FORMATS:
T002 | System Basics | End Users | eLearning | 1 hr |  |  |  | Planned | • eLearning
T003 | Advanced Features | Power Users | Lab | 4 hrs |  |  |  | Planned | • Workshop
T004 | [8 empty] | • Lab (hands-on)
T005 | [8 empty] | • Coaching (1:1)
T006
T007
T008
T009
T010
T011
T012
T013
T014
T015
T016
T017
T018
T019
T020
T021
T022
T023

## Sponsorship Tracker
Sponsorship Tracker | [6 empty] | INSTRUCTIONS
Track sponsor activities
Sponsor | Level | Activity | Target | Actual | Audience | Effect (1-5)
LEVELS:
Primary = Exec owner
Sustaining = BU leaders
Local = Dept managers

## Resistance Log
Resistance Log | [8 empty] | INSTRUCTIONS
Track resistance
ID | Date | Source | Type | ADKAR Gap | Severity | Mitigation | Owner | Status
R001 | [8 empty] | TYPES:
R002 | [8 empty] | Active = Vocal
R003 | [8 empty] | Passive = Silent
R004 | [8 empty] | Compliance = Motions
R005
R006 | [8 empty] | Link to ADKAR gap
R007
R008
R009
R010
R011
R012
R013
R014
R015
R016
R017
R018
R019
R020
R021
R022
R023
R024
R025

## KPI Dashboard
KPI Dashboard |  |  |  |  | INSTRUCTIONS
Track 6 key metrics
KPI | Target | Baseline | Current | Status
Awareness Level | 100% |  |  |  | Enter Baseline at start
Adoption Rate | 85% |  |  |  | Update Current regularly
Proficiency Level | 80%
Resistance Level | 10% |  |  |  | Status auto-calculates
Sponsor Engagement | 4
Sustainment Rate | 90%

## Maturity Assessment
Maturity Assessment |  |  |  | INSTRUCTIONS
Rate maturity 1-5
Dimension | Current (1-5) | Target (1-5) | Gap
Leadership & Sponsorship |  |  |  | 1 = Ad-hoc
Stakeholder Engagement |  |  |  | 2 = Emerging
Communication |  |  |  | 3 = Defined
Training & Development |  |  |  | 4 = Managed
Resistance Management |  |  |  | 5 = Optimized
Measurement & Analytics
Process Integration |  |  |  | Gap = Target - Current
Change Agent Network
Average:

## CSF Checklist
CSF Checklist |  |  |  | INSTRUCTIONS
Rate each CSF 1-5
# | Critical Success Factor | Rating (1-5) | Evidence/Notes
1 | Executive Sponsorship |  |  | 1 = Not addressed
2 | Clear Vision & Case |  |  | 2 = Minimal
3 | Stakeholder Engagement |  |  | 3 = Partial
4 | Effective Communication |  |  | 4 = Well done
5 | Training & Capability |  |  | 5 = Best practice
6 | Change Agent Network
7 | Resistance Management |  |  | Avg 4+ = Strong
8 | Measurement & Reinforcement |  |  | Avg <3 = At Risk
Average:

## Risk Register
Risk Register | [8 empty] | INSTRUCTIONS
Score = L × I
ID | Risk Description | Category | L (1-5) | I (1-5) | Score | Mitigation | Owner | Status
R001 | [8 empty] | 1-6 = Low
R002 | [8 empty] | 7-14 = Medium
R003 | [8 empty] | 15-25 = High
R004
R005 | [8 empty] | L = Likelihood
R006 | [8 empty] | I = Impact
R007
R008
R009
R010
R011
R012
R013
R014
R015
R016
R017
R018
R019
R020

## Change Impact
Change Impact | [7 empty] | INSTRUCTIONS
Document impacts
ID | Group | Impact Type | Severity | Description | Mitigation | Owner | Status
IMP001 | [7 empty] | TYPES:
IMP002 | [7 empty] | Process, Technology,
IMP003 | [7 empty] | Role, Skills, Culture
IMP004
IMP005 | [7 empty] | SEVERITY:
IMP006 | [7 empty] | High = Major change
IMP007 | [7 empty] | Low = Minor adjust
IMP008
IMP009
IMP010
IMP011
IMP012
IMP013
IMP014
IMP015
IMP016
IMP017
IMP018
IMP019
IMP020
IMP021
IMP022
IMP023
IMP024
IMP025